## Slide 1
Progress Report
Ian Evans
On behalf of the Chandra Source Catalog Project Team
Chandra Users’ Committee Meeting
October 23, 2014

## Slide 2: Summary
Summary of Progress Since Last CUC Meeting and Future Plan
  Completed algorithm development and implementation through source detection and evaluation (through “stacker” pipeline)
  Established simulation pipeline and evaluated results
  Purchased and deployed new hardware (2013 CUC recommendation)
  Recently completed major pre-production test run
    150 observation stacks
  Assembled and trained a volunteer science team (mostly outside CSC team) to review pipeline output
    Appreciate support of CXC director in doing this
  Propose to provide early release list of detections (based on 2013 CUC recommendation)
    Include at a minimum position + errors, likelihood, aperture photometry proxy
  Plan going forward
    Complete science test and incorporate feedback
    Complete current “open” tasks
    Start production — by end of 2014 (time to complete: several months)
    Provide initial list of detections (FITS format) to community — 2nd quarter 2015
    Run phase 2–3 pipelines — 2nd half of 2015 (time to complete; 1–2 months)
    Perform final (human review) QA — late 2015 (time to complete: ~ 1 month)
    Release full CSC version 2.0, all databases and data products

## Slide 3: Release 2: Science Highlights
Science Highlights Since Last CUC Meeting
  Continued evaluating data from numerous pipeline test runs and simulations
    Identified significant background-related issues/investigated possible solutions
      Adaptively smoothing the background addressed the core problem
    Evaluated performance of MLE point source fits (source position and amplitude)
      Appears to meet production requirements — ready for final science tests
    Evaluating ability to detect and classify “compact” (~1″–30″) non-point sources
      Have possible solution; detection efficiency is low
  Updated the simulation pipeline/constructing simulations as needed
    Injects sources with known properties into the data
    Simulations are useful for diagnosing issues and are required to set key production pipeline parameters (e.g., likelihood thresholds)
  Defined method to derive position error estimates using MCMC algorithm
    Still evaluating test results, but appears to produce good results for point sources
    Working on optimizing extended source fits
    Not a lien on production start — can be run as a “follow-on” pipeline after stacker pipeline if required
  Continuing development of specifications for post-detection phase pipelines
    Completed aperture photometry specifications
    Developed draft specifications for spectral fits
  Aperture photometry paper (Primini and Kashyap) accepted for publication by ApJ (Nov. 10 issue)

## Slide 4: Release 2: Software Highlights
Software Highlights Since Last CUC Meeting
  Continued developing/refining pipelines through stacker pipeline
    Corrected stacked-observation astrometry to exposure weighted aspect solution
    Developed new adaptive smoothing algorithm for background maps
      Ensures smoothing scale is sufficiently long on-axis (where PSF is small)
    Determined position error ellipses from per-detection fit statistic surfaces using pyBLoCXS MCMC algorithm in Sherpa
    Extensively investigated and refined algorithms based on science testing
    Identified and resolved bugs/unexpected issues as necessary
  Infrastructure updates
    Evaluated, received, and tested new processing cluster
      8 Dell R910 servers (total 320 cores, 4 TB memory, 43.2 TB local disk)
    Established simulation thread
    Rationalized archival file data products, contents, and file headers
    Integrated quality assurance pipelines and manual quality assurance GUI
    Migrated CSC archive infrastructure to 64 bit Linux
    Added automated population of web pages to assist review of test run results
  Science testing
    Continued to support extensive science testing through stacker pipeline
    Continued managing pipeline test runs and simulations
    Continued performing preliminary assessments of test runs prior to science review

## Slide 5: Release 2: Source Detection
The image compares source detections between rel. 1 and the expected performance for rel. 2, in a region of the Orion nebula (M42). The image is ~4′ across. Bright sources detected in both releases are indicated by magenta (rel. 2 likelihood, ℒ ≥ 15) or blue (9 ≤ ℒ < 15) circles. Green circles indicate rel. 2 sources with ℒ ≥ 15 not found in rel. 1, while yellow circles indicate rel. 2 sources with 9 ≤ ℒ < 15 not found in rel. 1. Red crosses mark detections from rel. 1 that were either not detected in rel. 2 or that have ℒ < 9 (and are therefore flagged as false).

## Slide 6: Release 2: Source Positions
For simulated point sources with more than 50 counts and 𝜃 < 3′ (left), the mean error in the fitted position is ~0.005″ in both α and δ, with an rms of ~0.05″. For 1″ extended sources (right), the mean error is comparable, but the rms is ~0.2″. Note that the scale for the plot on the right is a factor of 10 larger than that for the plot on the left.

## Slide 7: Release 2: Source Positions (cont.)
Source position errors in release 2 will be reported as 95% error ellipses computed using Sherpa’s get_draws pyBLoCXS MCMC based algorithm. The actual draws for each source and energy band will be recorded in archived data products. The example above shows the accepted draws for a point source located ~10′ off-axis with ~50 net counts in the broad energy band in a single observation.

## Slide 8: Release 2: Aperture Photometry
Correlation between broad-band amplitude of MLE point source fit and photon flux computed using full aperture photometry formalism for a sample of point sources. The correlation indicates that the MLE amplitude may be used as a proxy for aperture photometry of point sources in the short term.

## Slide 9: Release 2: Aperture Photometry (cont.)
Correlation between broad-band amplitude of MLE point source fit and event rate in the source aperture for a sample of point sources extends the correlation to the faintest detectable sources.

## Slide 10: For sources with more than 50 counts, with 𝜃 < 3′, the distribution of extent likelihood (i.e., the likelihood that an extended source fit is preferred over a point source fit) is well-separated for actual point and 1″ extended sources (top). For this range of 𝜃 and counts, an extent likelihood threshold of 20 yields a Type 1 error (mistaking a point source for an extended source) of << 1%, with a Type 2 error (missing a true extended source) of only a few percent (bottom).
Release 2: Extended Source Identification

## Slide 11: Release 2: Schedule Update
Schedule Status
  Schedule has slipped by ~6 months since the last CUC meeting
    Resource competition continues largely unchanged or is marginally worse
    Loss of key science/software staff has significantly impacted the schedule, particularly in areas of background determination and source fitting
    Unexpected issues with background determination, source detection and fitting took longer than anticipated to investigate and resolve due to loss of key staff
    Science algorithms through stacker pipeline now mostly in place
    Catalog processing performance issues have been resolved with new hardware
Example Schedule Impacts
  Acquired higher performance hardware following CUC recommendation
    Lack of obvious replacement candidate required careful evaluation of performance improvement to justify high cost
    Testing effort, purchase, and installation had a ~3 month impact on parts of the schedule
    Proven very worthwhile since testing and operations present a heavy load
  Unexpected network file server crashes
    To minimize risk to CXC operational threads, discontinued using catalog test system until a software update could be developed by the vendor and installed
    This ultimately took ~2 months

## Slide 12: Release 2: Production Schedule
Operations plan
  Phase 1: run through stacker pipeline
    Creates all per-stack source detections
    Steps to phase 1 production
      CAT 4.2.6 release
      Run “mini-test” with good results
      Run test of 150 stacks
      Complete science review I and feedback
      Set initial production parameters based on simulations
      CAT 4.2.7 release
      Run test of 400 stacks (performance test)
      Complete science review II and feedback
      Refine production parameters based on simulations and run of 400
      CAT 4.2.8 release
      Complete reprocessing of 2012 Sep–2014 Jun aspect data to fix ~0.4″ offset (scheduled for November)
    Production run through stacker, including auto and manual QA
    Run a posteriori position error determination pipeline if required
    Start production ~end 2014 (time to complete: several months)
    Propose to make the per-stack source detections available to the user community in FITS binary table format

## Slide 13: Release 2: Production Schedule (cont.)
Operations plan (cont.)
  Phase 2: run master_match pipeline
    Merges source detections from overlapping stacks and assigns source names
      Pipeline to be developed
      Source matching based on existing code from release 1
      New functionality to compute photometric upper limits
        Based on existing code from the release 2 pre-stacker, but spec not yet available
    Start production 2nd half 2015 (time to complete: ~ week)

## Slide 14: Release 2: Production Schedule (cont.)
Operations plan (cont.)
  Phase 3a: run source pipeline
    Computes source properties
      Pipeline to be developed
      Mostly based on release 1 code updated with enhanced functionality
        Aperture photometry — significant update to release 1 algorithms
          spec/tool development mostly complete
        Bayesian blocks observation partitioning — new functionality
          science prototype/draft spec exists
        Hardness ratios — revised to use PDFs from aperture photometry
          straightforward, but spec not yet available
        Spectral model fluxes and spectral fits — minor update to release 1
          draft spec exists (needs review)
        Temporal variability analysis — intra-observation minor update to release 1; inter-observation revised to use PDFs from aperture photometry
          straightforward, but spec not yet available
    Start production 2nd half 2015 (time to complete: ~ month)

## Slide 15: Release 2: Production Schedule (cont.)
Operations plan (cont.)
  Phase 3b: run master pipeline
    Merges properties for each unique source on the sky
      Pipeline to be developed
      Similar to merge processing from release 1 master pipeline
      Mostly uses components from the source pipeline with groups redefined, but spec not yet available
    Start production late 2015 (time to complete: ~ week)
  Phase 4: perform final (human review) QA
    All pipelines are followed by appropriate automated QA processing
      If automated QA detects a pipeline or data anomaly that requires human review, manual QA is invoked
    Manual QA can be forced after several critical pipelines if needed
    Almost all manual QA takes place during the actual pipeline production runs
    A set of “sanity check” final QA analyses are performed at the end of each production phase
    The phase 4 final review approves release 2.0 of the catalog
    Start production late 2015 (time to complete: ~ month)

## Slide 16: Release 2: Early Release Data
Initial List of Detections
  2013 CUC recommendation
    Consider staged releases, where certain parts of the sky might be released ahead of others
  We propose to make available an initial list of per-stack source detections as soon as practicable
    As a minimum, the list will include detection position and error, likelihood, and point source fit amplitude (proxy for aperture photometry) from MLE
    Additional categories of properties that could be included are
      Fit statistics and associated fit metrics
      Parameterized fits to “compact” (extended by a few arcsec) detections
      wavdetect and mkvtbkg candidate point/compact detections input to MLE
      Extended source convex-hull polygons
    However, these properties are primarily intended for debugging and QA
      With the exception of source position and amplitude for isolated point sources, they may not correlate well with actual physical source properties, and many of the candidate detections will be false
  Input on whether any of these additional properties from these categories should be included in the initial list of per-stack detections is welcome
    We would minimally validate the additional properties prior to release

## Slide 17: Release 2: Software Releases
CSC 2.0 Catalog Production-Related Releases
Release | Date | Content
CAT 4.1.2 | 04 Dec | Additions to PLs (tune algorithm params, crater detection, add ultrasoft band); 2nd tier MLE updates; data product refinements
CAT 4.1.3 | 31 Jan | Reviewed and updated file headers; number of tuning upgrades to PL parameters; set w band PSF scale param; increased bkg source exclude param by 10%; added source position error ellipse to MLE output
CAT 4.1.4 | 06 Feb | Migrate archive CAT builds to 64 bit; add new archive server capability to handle CSC Rel. 2 data; few CSCview bugfixes
CAT 4.1.5 | 15 Feb | Initial integration of QA; MLE bkg changes
CAT 4.1.6 | 04 Apr | Fixed the issue with bright positions in dim bkgds; integrated crates updates and bug fixes into PL; increased speed when writing mrgsrc3 files with many rows
CAT 4.1.7 | 12 Apr | Migrate CIAO 4.6 code base and OTS to CSC
CAT 4.2 | 06 Aug | QA thru stacker; reprocessing support; interleave-mode; performance tuning; upgrade compiler to gcc 4.8
CAT 4.2.1 | 29 Jul | CAT integ issues (QA, repro); several upgrades from science PLs

## Slide 18: Release 2: Software Releases (cont.)
CSC 2.0 Catalog Production-Related Releases (cont.)
Release | Date | Content
CAT 4.2.2 | 12 Sep | New adaptive smoothing for backgrounds; fix to MLE for off center points; ability to add user exclusion regions; update to repro script to no longer create sexp3; MLE fix from regression in positions; MLE get_draws added
CAT 4.2.3 | 29 Sep | MLE valid flag and NULL case handling; lower risk updates/bugfixes from PL
CAT 4.2.4 | 30 Sep | Upgrade CAT archive servers to linux
CAT 4.2.5 | 01 Oct | Science test must-haves; lower priorities if they fit schedule
CAT 4.2.6 | 17 Oct | Address SAOTrace call issue; 0 counts on CCD (corner case)
CAT 4.2.7 | ~15 Nov CF | Lower priority RFEs/bugfixes; feedback from science test I
CAT 4.2.8 | ~01 Dec CF | Remaining science priorities; feedback from science test II Production run through stacker PL
CAT 4.3 | 2nd half 2015 | master_match and source PLs; limiting sensitivity population Production run master_match and source PLs
CAT 5.0 | Late 2015 | master PL; populate databases Production run master PL, final QA review, and release

## Slide 19: Current Catalog Release: Statistics
Summary
  Catalog version: 1.1; Released: 2010 Aug 10
    106,586 master sources
    158,071 source detections
    5,110 observations with at least one detected source
  Subset of master source properties are available via HEASARC Browse/Xamin, NED, and Vizier services
    Usage statistics reported below do not include accesses via these services
Usage Statistics
* Excludes 198K searches (~ all non-CfA) from 2014 May; ** Excludes 99K searches (~ all non-CfA) from 2014 June
Release 1.1 | Current Reporting Period 2014 Apr 01 – 2014 Sep 31 |  | Previous Reporting Period 2013 Oct 01 – 2014 Mar 31 | 
 | Number | % Non-CfA | Number | % Non-CfA
CSCview catalog browser initializations | 163 /month | 86% | 158 /month | 82%
CSCview catalog browser properties searches | 140 /month | 87% | 180 /month | 82%
Command-line (CLI) searches | 3455 /month* | 81% | 687 /month | 20%
VO cone searches | 2986 /month** | ~100% | 5209 /month | 99%
CSC Sky in Google Earth | 575 visits/month |  | 520 visits/month | 

## Slide 20: Current Catalog Release: Support
CSCview
  Released two updated versions of CSCview including several bug fixes and enhancements
    Third update currently being tested
3rd Party Interfaces to CSC Release 1.1
  Master-source table “basic summary properties” (only) have been available via NED since 2011
  CDS has recently made these data available through Vizier
  HEASARC has made the master-source table available through their browse/Xamin interface
    HEASARC does not provide access to the source-by-observation table or any catalog FITS file-based data products
    HEASARC has changed the names of many of the columns, as well as the name and designation of the broad energy band
      They are no longer consistent with either the full CSC release at CXC or with the published CSC paper (however the changes are documented)